## Quote Comparison
PETERSON SOLAR PROJECT — SUPPLIER QUOTE COMPARISON
Updated: April 20, 2026 ¦ All prices FOB China unless noted
SOLAR PANELS
# | Supplier | Model | Watts | Qty | Unit Price | Total | $/Watt | Bifacial | Warranty | Notes
1 | Sunpal Power (both quotes) | SP630M-66H TOPCon Bifacial | 630 | 48 | 76 |  |  | Yes | 30 yr | Included in both Atess & Megarevo packages
2 | Simone Wang (TBD company) | TBD — bundled w/ tracker | 550 |  |  |  |  | Ask | Ask | Panels bundled w/ 8-panel dual-axis tracker @ $3,250/unit
DUAL-AXIS TRACKER POSTS
# | Supplier | Model/Config | Panels/Post | Qty Posts | Unit Price | Total | $/Panel Slot | Wind Stow | Warranty | Notes
1 | Simone Wang (TBD) | 8-panel dual-axis post | 8 | 7 | 3250 |  |  | Ask | Ask | INCLUDES panels! 7 posts × 8 panels = 56 panels. Price is tracker+panels bundled
2 | TBD — RFQ sent | 2-panel dual-axis post | 2 | 30 |  |  |  | 40mph/stow 50+ | 10yr struct | Per our RFQ to Kseng, PromiSteel, HDsolar, Huayue, Xinpeng
3 | TBD — RFQ sent | 4-panel dual-axis post | 4 | 14 |  |  |  | Ask | Ask | 4-panel config per supplier drawing (4578mm frame)
4 | Sunchaser / Shandong Zhaori | ZRD 8-panel dual-axis | 8 | 7 |  |  |  | 40 m/s stow | 3 yr ext. | TUV SUD + CE. IP65. RS485+wireless. PRICE NOT YET — datasheet only.
5 | Huayue / Shandong Huayue | HYS-8PV-78-LSD (or -144) | 8 | 7 |  |  |  | Ask | Ask | Drawing only. Filename says 144, drawing says 78 — MODEL CONFUSION.
6 | Sunchaser / Shandong Zhaori | ZRD 10-panel dual-axis | 10 | 6 |  |  |  | 40 m/s stow | 3 yr ext. | Alt sizing. 10 panels ≤26m².
7 | Simone Wang (panels + tracker) | 8-panel bundle (company TBD) | 8 | 7 | 3250 |  |  | Ask | Ask | BUNDLE includes panels. COMPANY NAME STILL UNKNOWN.
INVERTER + BATTERY STORAGE (ESS)
# | Supplier / Quote | Inverter | Inv. kW | Battery kWh | Inverter $ | Battery $ | Total ESS $ | $/kWh | Certs | Notes
1 | Sunpal — Atess Quote | Atess HPS30000TL-US-208 3-Phase | 30 | 61.44 | 4880 | 8400 |  |  | Ask UL1741 | 3 MPPT, 190-240V. HIGH VOLTAGE battery (614V). 100% TT upfront
2 | Sunpal — Megarevo Quote | 2× Megarevo R16KLNA Split-Phase | 32 | 64 | 4900 | 6300 |  |  | UL Cert | Split-phase 120/240V ✓ US-spec! 4× 16kWh floor batteries + combiner box
3 | Japower All-in-One ESS | Built-in (per unit) | 30 | 80 |  |  |  |  | Ask UL1741 | All-in-one cabinet. Need direct quote — Alibaba doesn't show real price
4 | Japower × 2 (Tier 3) | Built-in (paralleled) | 60 | 160 |  |  |  |  | Ask UL1741 | 2 units paralleled for full off-grid. Est. $18K-$28K total
5 | Sunwave (from PPTX) | Separate inv + battery | [6 empty] | Ask | Presented pros/cons of separate vs all-in-one. No pricing in deck.
6 | Sunwave — RIGHT-SIZED (Tier 3) | 2× SEI-18K-USP split-phase | 36 | 160.8 | 6084 | 13080 |  |  | CSA C22.2 107.1 | ⭐ LEADING. 2× inv + 10× SW-LCT-16. Off-grid capable, gen AC input. $19,164 FOB
7 | Sunwave — AS-QUOTED | 4× SEI-18K-USP split-phase | 72 | 192 | 12168 | 15696 |  |  | CSA C22.2 107.1 | Oversized. $27,864 FOB. Use unit prices from right-sized quote.
8 | Japower Opt 1 (Laura) × 2 | 2× SRNE 18kW split-phase | 36 | 160 |  |  | 26000 |  | UL (claimed) | 2× $11,999 = $26,000 FOB. +$2,000 outdoor adder. All-in-one integrated.
9 | Japower Opt 3 (Laura) × 2 | 2× Solis 30kW split-phase | 60 | 200 |  |  | 39998 |  | Ask UL | 2× $19,999. Larger headroom, commercial option.
10 | LongKun (Zoey Mai) | 1× 30kW HV hybrid | 30 | 40 | 5381 | 10022 |  |  | UL1973/UL9540A (batt) | RIGHT-SIZED: 1 inv + 1 cab. Full quote 10 cabs + 5 inv = $127K. Split-phase NOT confirmed.
11 | Kamada (James Tang) — 1 set | 1× 15kW×2 split-phase | 15 | 16 | 3885 | 7115 |  |  | Ask UL | PER-SET. Full quote 6 sets = $74,500 DDP (incl. $8,500 ship). Sizing math unclear.
12 | GSL Energy (Alex Yan) — BATTERY ONLY | — |  | 157.6 |  | 17710 | 17710 |  | REPT Grade A, UL ask | 157.6 kWh (11× 14.33kWh). NEEDS INVERTER (LV bus, 51.2 V). No inverter offered.
13 | GSL batt + Sunwave inv — PAIRED | 2× Sunwave SEI-18K-USP | 36 | 157.6 | 6084 | 17710 |  |  | CSA + REPT | HYPOTHETICAL. $23,794 FOB. Sunwave inv is LV-compatible with GSL 51.2 V stacks.
FULL SYSTEM PACKAGE COMPARISON (Tier 3 Scale: ~30kW / 48-56 panels)
# | Package Option | Panels | Tracker | Inverter+Battery | BOS+Cable | Total FOB | Est. Freight | Est. Tariffs | Landed Cost | Notes
1 | Sunpal + Atess + Separate Trackers | 3648 |  | 13280 | 2330 |  | 3500 |  |  | No tracker quote yet. Atess inverter is 3-PHASE not split-phase — may not work for US residential 120/240V!
2 | Sunpal + Megarevo + Separate Trackers | 3648 |  | 11200 | 2530 |  | 3500 |  |  | BEST US SPEC: Megarevo is split-phase 120/240V with UL cert. Missing tracker pricing.
3 | Simone Wang Bundle + Megarevo ESS |  | 22750 | 11200 | 2000 |  | 3500 |  |  | Tracker price INCLUDES panels (7×$3,250). Need Megarevo ESS separately.
4 | Simone Wang Bundle + Japower ESS ×2 |  | 22750 |  | 2000 |  | 3500 |  |  | Waiting on Japower pricing. All-in-one = simplest install.
5 | ⭐ Sunpal panels + Sunwave right-sized + Sunchaser trackers | 3648 |  | 19164 | 2000 |  | 3500 |  |  | Best off-grid Tier 3 stack. Needs Sunchaser/Huayue tracker price. Mode A compatible.
6 | Simone Wang bundle + Sunwave right-sized ESS | 22750 |  | 19164 | 2000 |  | 3500 |  |  | Simplest IF Simone's specs + company name check out.
7 | Sunpal panels + GSL batts + Sunwave inv + Sunchaser tracker | 3648 |  | 23794 | 2000 |  | 3500 |  |  | Best battery $/kWh IF GSL certs check out. Mixed-ecosystem risk.
8 | Kamada 1-set DDP + Sunpal panels + Sunchaser tracker | 3648 |  | 12417 | 2000 |  | 0 |  |  | Kamada single-set DDP ≈ $12,417/set (quote was 6 sets $74,500 DDP incl $8,500 ship). ONLY if 15 kW×2 split-phase verified.

## US Tariff Reference
US TARIFF RATES ON CHINESE SOLAR EQUIPMENT (2025-2026)
Component | Section 301 Rate | AD/CVD Rate | Notes / Status
Solar Panels/Cells (from China) | 50% | 15-50% additional | Section 301 raised to 50% Sep 2024. Plus AD/CVD duties from 2012 cases. HIGHEST tariff category.
Solar Panels (SE Asia assembly) | Varies 24-46% | New AD/CVD pending (Jun 2025) | Cambodia, Malaysia, Thailand, Vietnam. ITC final ruling Jun 2, 2025. Could add 15-50% more.
LiFePO4 / Lithium Batteries (non-EV) | 25% (effective Jan 2026) | N/A currently | Already increased from 7.5% to 25% as of Jan 2026. This is the CURRENT rate. Total with other duties could reach ~82%.
Hybrid Inverters (HTS 8504.40) | 25% | No specific AD/CVD | Classified as static converters. Section 301 List 3 at 25%. Some exclusions may apply — check HTS.
Solar Trackers / Mounting Systems | 25% | No specific AD/CVD | Steel/aluminum structures. Section 301 List 3. Plus Section 232 steel/aluminum tariffs may apply.
All-in-One ESS (battery+inverter) | 25-50% (classification dependent) | Unclear — new product category | Could be classified as battery (7.5-25%) or inverter (25%) or mixed. Customs broker needed.
PV Wire / Cables | 25% | N/A | Section 301 List 3. Consider sourcing locally — heavy and cheap in US.
Section 201 Safeguard (panels) | 14% (expires Feb 2026) | Stacks on top of above | Applies to ALL imported panels regardless of origin. Expires Feb 7, 2026.
CRITICAL NOTES:
1. PANELS have the HIGHEST tariff exposure (50-100%+). Simone Wang's bundled tracker+panel deal may help if panels ship as 'tracker system' vs 'solar modules' — discuss with customs broker.
2. BATTERIES are currently cheapest to import (7.5%) but rising to 25% in 2026. Order batteries ASAP if going separate.
3. ALL-IN-ONE ESS units (Japower) have ambiguous classification — could be favorable if classified as 'energy storage system' vs 'battery' or 'inverter'. Customs broker ruling critical.
4. The Megarevo split-phase inverter has UL certification — this is the only quote so far with confirmed US electrical certification.
5. Anti-dumping duties apply to PANELS specifically — inverters, batteries, and trackers do NOT have specific AD/CVD orders (as of Apr 2026).
6. CONSULT A CUSTOMS BROKER before ordering. HTS classification determines which tariffs apply. Wrong classification = penalties.

## Battery-Inverter Price List
BATTERY & INVERTER COMPONENT PRICING (from supplier image)
Item | Model | Description | Qty Left | 1-5pcs | 6-20pcs | >50pcs | kWh | $/kWh (1-5)
1 | A0189-1 51.2V/300AH | 51.2V/300AH Stack w/ JY BMS | 10 | 1233 | 1182 | 1131 | 15.36
2 | A0189-1 51.2V/325AH | 51.2V/325AH Stack w/ JY BMS | 8 | 1366 | 1309 | 1252 | 16.64
3 | A0189-3-2 51.2V/320AH | 51.2V/320AH Stack w/ JK BMS, 2A active balancing, 4.3in screen | 12 | 1397 | 1339 | 1281 | 16.38
4 | A0182-3-3 51.2V/325AH | 51.2V/325AH Tower & 5in Touch Screen, SOC Light Strip | 6 | 1397 | 1339 | 1281 | 16.64
5 | A0182-2-2 51.2V/300AH | 51.2V/300AH Bottom unit | 2 | 1239 | 1187 | 1135 | 15.36
6 | A0182-2-2 51.2V/320AH | 51.2V/320AH Bottom unit | 3 | 1376 | 1319 | 1261 | 16.38
7 | A0182-3-3 51.2V/325AH | 51.2V/325AH Tower-JK | 1 | 1397 | 1339 | 1281 | 16.64
8 | A0207 51.2V/100AH | 51.2V/100AH Wall Mounted Battery | 5 | 525 | 505 | 485 | 5.12

## Decision Tracker
OPEN DECISIONS & ACTION ITEMS
Decision / Action Item | Status | Owner | Notes
Get Simone Wang's company name | WAITING | Andrew | She quoted $3,250 for 8-panel dual-axis tracker w/ panels
Confirm Simone's panel specs | WAITING | Andrew | What brand/wattage panels? Bifacial? TOPCon? Need specs to compare.
Get Japower direct quote (US spec) | WAITING | Andrew | 80kWh/30kW, 120V/240V 60Hz, qty 2. Alibaba price doesn't update.
Atess inverter: 3-phase vs split-phase? | RED FLAG | Andrew | HPS30000TL-US-208 is 3-phase 190-240V. US residential is split-phase 120/240V. May NOT work!
Contact customs broker for HTS codes | NOT STARTED | Andrew | Critical for tariff planning. Panels vs tracker vs ESS classification.
Decide: separate components vs all-in-one ESS | OPEN | Andrew/Roger | Sunwave PPTX laid out pros/cons. Separate = more flexible but complex. All-in-one = simpler but locked in.
Decide: 2-panel vs 4-panel vs 8-panel tracker config | OPEN | Andrew | 8-panel from Simone is cheapest per panel slot. 4-panel per supplier drawing. 2-panel in original design.
Get tracker RFQ responses | WAITING | Andrew | RFQs sent to Kseng, PromiSteel, HDsolar, Huayue, Xinpeng
Battery tariff already at 25% (since Jan 2026) | MISSED | Andrew | LiFePO4 tariff already went from 7.5% → 25% in Jan 2026. Current rate applies. Factor 25% into all battery pricing.
Verify all equipment UL/IEEE certifications | NOT STARTED | Andrew | Only Megarevo confirmed UL cert so far. Need UL1741 + IEEE 1547 for grid interconnection.
LongKun (Zoey Mai): right-size quote | WAITING | Andrew | Quote was 400 kWh/150 kW — ~2.5× Tier 3. Ask for 1 inv + 1 cabinet. Also confirm split-phase 120/240 V on 30 kW 'US Standard' inverter.
LongKun: validity expires 2026-04-23 (7 days) | URGENT | Andrew | Reply before then. 100% T/T upfront — negotiate 50/50.
Kamada (James Tang): decode 15 kW×2 + 5-parallel sizing | WAITING | Andrew | Ambiguous: inverter 15 kW or 30 kW? Battery pack 16 kWh total or 80 kWh? Quote is 6 sets — unclear what a 'set' is.
Kamada: validity expires 2026-04-22 (5 days) | URGENT | Andrew | Only DDP quote on the table — apples-to-apples landed cost.
Kamada: UL/UL9540 cert docs for inverter + battery | WAITING | Andrew | Required before any order.
GSL (Alex Yan): inverter pairing plan | INFO | Andrew | GSL sells 51.2 V LV batteries only. Must pair with LV-bus inverter (Sunwave SEI-18K-USP, SolArk, SRNE). NOT compatible with LongKun HV 160-800 V or Kamada HV.
GSL: confirm UL1973/UL9540A + protocol list | WAITING | Andrew | Need specific protocol list (Pylontech/CAN/Victron/etc.) so Sunwave/SRNE compatibility is confirmed.
GSL: DDP-to-Erda shipping add-on | WAITING | Andrew | For apples-to-apples with Kamada DDP.
GSL: duplicate quote file (x2) | INFO | Andrew | Same PDF arrived twice (and (1)). Only one to track.
Sunchaser / Zhaori (ZRD): request formal PI | NOT STARTED | Andrew | Have datasheet only. Ask 7×8-panel OR 6×10-panel, EXW + DDP, lead time, wind/snow certs for Utah.
Huayue (HYS-8PV): clarify 78 vs 144 model + get PI | NOT STARTED | Andrew | Filename HYS-8PV-144-LSD, drawing HYS-8PV-78-LSD. Ask which they offer; get price.
Bill of Lading (Kenny → james riley, 10/30/2025) | FLAG | Andrew | Unrelated to Peterson Solar? Names don't match. Clarify whether this belongs here.
Sunwave (Fred): send the drafted email | DRAFTED | Andrew | Email_to_Fred_Sunwave.md ready. 5 questions: off-grid mode, gen AC input, paralleling, pump LRA tolerance, any UL beyond CSA.
Battery $/kWh normalized comparison | ANALYSIS | Claude | Sunwave $81/kWh · GSL $112/kWh · LongKun $250/kWh (HV cab premium) · Kamada $445/kWh (sizing unclear — likely wrong). See ANALYSIS.md.
Tracker config: 8 vs 10 vs 4 panels | OPEN | Andrew | Revisit once pump load + panel wattage settled.